## Madhuri Vemulapaty
Agile Task Board
Assigned To: | Madhuri Vemulapaty
Use Case: | Product and Sales Person
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Creation of Virtual Machines | 2 | 2.5 | 2019-11-04 | 2019-11-04 | Could not connect to the IP of the virtual machine due to internal settings in the Citrix system.
Changes in the existing MVC project | 2.5 | 2.5 | 2019-11-04 | 2019-11-04 | Added confirmation pop-ups to submit buttons, incorporated pagination, search and sort in tables.
Creation of SQL Database in Azure | 1 | 1 | 2019-11-05 | 2019-11-05 | The SQL Database and related resources were created successfully.
Creation of tables and stored procedures from existing scripts | 1 | 1.5 | 2019-11-06 | 2019-11-06 | Could not access the database from designated system so had to use the Trainer's system.
Learning to create and use Cosmos DB | 2 | 2 | 2019-11-07 | 2019-11-07 | Deleted due to limited subscription access
Deploying MVC application on Azure App services | 2 | 2 | 2019-11-07 | 2019-11-07 | Deleted due to limited subscription access
Creating and using Http trigger function through Azure function App | 2 | 2.5 | 2019-11-06 | 2019-11-06 | Debugging errors in the function.
Using function to perform CRUD operation on SQL Database | 1.5 | 1.5 | 2019-11-08 | 2019-11-08 | CRUD operations on the existing tables in the database.
Creating Azure web Cognitive services | 2 | 2 | 2019-11-08 | 2019-11-08 | Auto Suggest service was created.
Creating HTML page to consume the Cognitive services - Auto Suggest | 1 | 1 | 2019-11-09 | 2019-11-09 | HTML page consists of a search box to search a word. The results of Auto Suggest are displayed in JSON format.
Code to populate the results of Auto Suggest in the drop down list of search | 0.75 | 0.75 | 2019-11-09 | 2019-11-09 | The results are displayed in the drop down.
Create and use Blob service | 1 | 1 | 2019-11-09 | 2019-11-09 | Used the blob storage to upload files.
Create Queues in Azure | 1 | 1 | 2019-11-11 | 2019-11-11 | Stored messages in the queues
Creating Web API in Visual Studio | 1 | 1.5 | 2019-11-12 | 2019-11-13 | Designing the web page consumed more time. Errors while incorporating pagination.
Creating a Logic App in Azure to connect a queue and table | 1 | 1.5 | 2019-11-13 | 2019-11-13 | Debugging errors in the logic app
Deploying Web API in Azure |  |  | 2019-11-14 | 2019-11-14

## Ankush Agrawal
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Virtual machine created on azure. | 2 | 2.5 | 2019-11-04 | 2019-11-04 | Problem faced in connecting to virtual mchine due to firewall settings of citrix
Made changes to the existing MVC Project | 2.5 | 2.5 | 2019-11-04 | 2019-11-04 | Added the required summary comments, pagination, sorting and search to the tables
Sql Database Storage was created on azure | 1 | 1 | 2019-11-05 | 2019-11-05 | SQL Database and resource group was created succesfully.
Creation of the required tables, schema, stored procedures in Cloud SQL | 1 | 1.5 | 2019-11-06 | 2019-11-06 | The database on cloud wasn't accessible from the assigned machine. The script was run from the trainer's system.
Cosmos DB was learnt and created | 2 | 2 | 2019-11-07 | 2019-11-07 | Cosmos DB ws created and deleted. Since the money was being charged and limited funds available.
Deploying MVC application on azure app services. | 2 | 2 | 2019-11-07 | 2019-11-07 | MVC application was deployed and deleted. Since the money was being charged and limited funds available.
Creating and using Http trigger function through Azure function App | 2 | 1.45 | 2019-11-06 | 2019-11-06 | Created a function app on azure and used it ithe browser. It was deleted as well.
Using function to perform CRUD opertion on SQL Database | 2.5 | 2.75 | 2019-11-08 | 2019-11-08 | Initially faced problem on how to use connection string.
Using the function app in the local mvc application using CORS | 0.5 | 0.45 | 2019-11-08 | 2019-11-08 | Using the created functions in the mvc by giving permission through CORS.
Creating azure web cognitive services. | 2 | 2 | 2019-11-08 | 2019-11-08 | Services like autopredict were learnt.
Creating HTML page to consume the Cognitive services - Auto Suggest | 1 | 1 | 2019-11-09 | 2019-11-09 | Using the auto predict in a html page.
Code to populate the results of Auto Suggest in the drop down list of search | 0.75 | 0.75 | 2019-11-09 | 2019-11-09
Create Queues in Azure | 1 | 1 | 2019-11-11 | 2019-11-11
Creating and working with blob storage | 0.5 | 0.5 | 2019-11-12 | 2019-11-12
Creating Web API in Visual Studio | 1 | 1.5 | 2019-11-12 | 2019-11-13 | Initial problem faced wth ajax calls and how to handle json format.
Creating a Logic App in Azure to connect a queue and table | 1 | 1 | 2019-11-13 | 2019-11-13
Demo for load balancing and controlling traffic | 1 | 1 | 2019-11-13 | 2019-11-13
Documented the web API | 1 | 1 | 2019-11-13 | 2019-11-13

## Sourav Maji
Agile Task Board
Assigned To: | Sourav Maji
Use Case: | Return and Cancel
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Corrections in MVC Project | 2 | 3 | 2019-11-04 | 2019-11-04
Introduction to Azure and Creation of Virtual Machines | 2 | 3 | 2019-11-04 | 2019-11-04 | Added confirmation pop-up before each crud operations, Pagination to include searching and sorting
SQL Database creation in Azure | 1 | 1 | 2019-11-05 | 2019-11-05 | The SQL Database and related resources were created successfully.
App Service Creation | 1 | 1 | 2019-11-06 | 2019-11-06 | Created app service and Deleted the resource due to limited subscription.
Active Directory Creation | 2 | 2 | 2019-11-07 | 2019-11-07
CosmosDB Creation | 2 | 2 | 2019-11-07 | 2019-11-07
MVC Application Publish in Azure | 2 | 3 | 2019-11-07 | 2019-11-07 | Deploying the MVC application in Azure , few problems due to connection string.
Creating Function App through Azure App Creation | 1 | 1 | 2019-11-08 | 2019-11-08
Learning to perform CRUD operations via Azure | 2.5 | 3 | 2019-11-08 | 2019-11-08 | Performing Add, Get, Update, Delete operations in Azure. Issue in Database.
Creating Azure Web Cognitive Services | 1 | 1 | 2019-11-09 | 2019-11-09 | HTML page consists of a search box to search a word. The results of Auto Suggest are displayed in JSON format.
Writing JavaScript code to save the key as cookie and creating drop down as result | 2 | 2 | 2019-11-09 | 2019-11-09 | The results are displayed in the drop down.
Creating Queues in Azure | 1 | 1 | 2019-11-12 | 2019-11-12 | Stored messages in the queues
Demo for Logic App in Azure | 1 | 1.5 | 2019-11-13 | 2019-11-13
Developing web api and deploying it in azure | 3 | 4 | 2019-11-14 | 2019-11-14 | Problems faced due to mishandling of ajax format. A few pagination error.