## Sarthak Lav
Agile Task Board
Assigned To: | Sarthak Lav
Use Case: | Retailer
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Retailer
Create SQL Server table named "Retailer" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create RetailerService using Angular for CRUD operations | 2 | 3 | issue with fakedb, array handling and objects
UI - Create Angular Component & Template for "Retailer Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Create Retailer Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Edit Retailer Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Retailer Page" using Bootstrap & Angular | 1 | 1.5

## Sourav Maji
Agile Task Board
Assigned To: | Sourav Maji
Use Case: | Return and Cancel a Product
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours
Order Return
Create SQL Server table named "Return" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create ReturnService using Angular for CRUD operations | 2 | 2.5 | issue with fakedb, array handling and objects
UI - Create Angular Component & Template for "Return Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Place Return Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Return Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Return Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Cancel Order Page" using Bootstrap & Angular | 2 | 2.5
ReturnDetails
Create SQL Server table named "ReturnDetails" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create ReturnService using Angular for CRUD operations | 2 | 2 | issue with fakedb, array handling and objects
UI - Create Angular Component & Template for "Return Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Place Return Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Return Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Return Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Cancel Order Page" using Bootstrap & Angular | 2 | 2

## Madhuri Vemulapaty
Agile Task Board
Assigned To: | Madhuri Vemulapaty
Use Case: | SalesPerson, Product
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Products
Create SQL Server table named "Products" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 2
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3 | character casing mistakes, array handling and objects
UI - Create ReturnService using Angular for CRUD operations | 2 | 3
UI - Create Angular Component & Template for "Add Products Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Delete Products Page" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "UpdateProducts Page" using Bootstrap & Angular | 1 | 2
Create Salesperson
Create SQL Server table named "SalesPeople" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create Angular Component & Template for "Add Sales person Page" using Bootstrap & Angular | 2 | 2 | character casing mistakes, array handling and objects
UI - Create Angular Component & Template for "Delete Sales person Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Sales Person Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Sales Person Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "View Sales Person Sales' history" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Upload offline order" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Check Targets" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Cancel Offline Order" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Return Offline Order" using Bootstrap & Angular | 1 | 1

## Ankush Agrawal
Agile Task Board
Assigned To: | Ankush Agrawal
Use Case: | Orders
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Order
| 1 | 1.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel MSUnit for all CRUD operations | 2 | 2.5 | issue with fakedb, array handling, routing and objects
Prepare Test Cases using MSUnit test cases for all CRUD operations | 3 | 4
UI - Create OrderService using Angular for CRUD operations | 2 | 2
UI - Create Angular Component & Template for "Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Create/Edit/Delete Online Order Page" using Bootstrap & Angular | 5 | 6
UI - Create Angular Component & Template for "Order Details" using Bootstrap & Angular | 3 | 4
Ankush here
Create SQL Server table named Order and OrderDetails(Represents Cart) | 1 | 1
Created Stored Procedures for order and order Details for all CRUD Operations. | 2 | 2.5
Prepare test cases on C# sonsole application. | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
UI - Create OrderService using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Order Page" using Bootstrap & Angular | 4 | 4
UI - Create Cart and Empty Cart functions | 3 | 3
UI-Add product specific addreses. | 2 | 1.5

## Shreyash Pandey
Agile Task Board
Assigned To: | Shreyash Pandey
Use Case: | Address and Admin
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Admin
Create SQL Server table named "Admin" | 0.5 | 0.5
Prepare Test Cases using Excel MSUnit for all operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all operations | 1 | 1
UI - Create AdminService using Angular for Retrive and Login operations | 2 | 2.5 | issue with concept and silly mistakes in character casing
UI - Create Angular Component & Template for "Admin Login" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Update Discount" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Update Target" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Update Bonus" using Bootstrap & Angular | 1 | 1
Create Address
Create SQL Server table named "Address" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create AddressService using Angular for CRUD operations | 1 | 1 | issue with concept and mistakes in character casing
UI - Create Angular Component & Template for "Address Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Address Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Address Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Address Page" using Bootstrap & Angular | 1 | 1.5
Create Report
Create BL for "Report" as ReportBL | 1 | 1
UI - Create Angular Component & Template for "Retailer Order Report" using Bootstrap & Angular | 1 | 1
UI - Create Angular Component & Template for "Sales Person Order Report" using Bootstrap & Angular | 1 | 1