## Madhuri Vemulapaty
Agile Task Board
Assigned To: | Madhuri Vemulapaty
Use Case: | Product and Sales person
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Introduction to DevOps | 2 | 3 | 2019-11-16 | 2019-11-16 | We were introduced to DevOps and it took time in giving access to each team
Continuous Integration and Continuous Deployment | 1 | 1 | 2019-11-16 | 2019-11-16
Introduction to Agile | 1.5 | 1.5 | 2019-11-18 | 2019-11-18 | We were introduced to Agile methodology and relevant concepts like sprints, backlogs and other mandatory terms of Scrum
Creating the necessary PLP Documents | 2 | 3 | 2019-11-19 | 2019-11-19 | There were certain documents like TEAM_URS, TEAMREGISTER, MINUTESOFMEETING, PRODUCTBACKLOG, SPRINTBACKLOG which are necessary in Agile Methodology. We documented these for this sprint
Creating WebAPI and consuming it in MVC application | 4 | 5 | 2019-11-20 | 2019-11-21 | Created WebAPI for GetAllProducts, GetProductByProductID, Create method to add a new product.
Deploying the MVC Project in Azure | 2 | 2 | 2019-11-21 | 2019-11-21 | There were issues with the commit limits and WebAPI stopping in between due to limited Azure resources.

## Ankush Agrawal
Agile Task Board
|  | Assigned To: | Ankush Agrawal
|  | Project: | Great Outdoors
|  | Use Case: | Order Module
|  | Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Introduction to DevOps | 2 | 3 | 2019-11-16 | 2019-11-16 | We were introduced to DevOps and it took time in giving access to each team
Creating WireFrame for the project | 0.5 | 0.5 | 1900-01-15 | 1900-01-15 | Wire frame for few pages was created.
Introduction to Agile | 1.5 | 1.5 | 2019-11-18 | 2019-11-18 | We were introduced to Agile methodology and relevant concepts like sprints, backlogs and other mandatory terms of Scrum.
Deploying MVC Project on Dev Ops | 1 | 1.5 | 2019-11-18 | 2019-11-18 | Faced many release and build errors. Deployed it for continuous integration.
Creating the necessary PLP Documents | 2 | 2 | 2019-11-19 | 2019-11-19 | There were certain documents like TEAM_URS, TEAMREGISTER, MINUTESOFMEETING, PRODUCTBACKLOG, SPRINTBACKLOG which are necessary in Agile Methodology. Documented the Product Backlog.
Creating WebAPI and consuming it in MVC application | 4 | 5 | 2019-11-20 | 2019-11-21 | Created WebAPI for orders module and to create an order. There were issues in consuming POST API while doing for first time.

## Sourav
Agile Task Board
Assigned To: | Sourav Maji
Use Case: | Return and Cancel
Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Introduction to DevOps | 2 | 3 | 2019-11-16 | 2019-11-16 | We were introduced to DevOps and it took time in giving access to each team
Continuous Integration and Continuous Deployment | 1 | 1 | 2019-11-16 | 2019-11-16
Introduction to Agile | 1.5 | 1.5 | 2019-11-18 | 2019-11-18 | We were introduced to Agile methodology and relevant concepts like sprints, backlogs and other mandatory terms of Scrum
Creating the necessary PLP Documents | 2 | 3 | 2019-11-19 | 2019-11-19 | There were certain documents like TEAM_URS, TEAMREGISTER, MINUTESOFMEETING, PRODUCTBACKLOG, SPRINTBACKLOG which are necessary in Agile Methodology. We were new to it, so initially we were a bit confused what to write in which document
Creating WebAPI and consuming it in MVC application | 2 | 2.5 | 2019-11-20 | 2019-11-21 | We had to create WebAPI and had to perform CRUD operation on our respective user stories. I created get in WebAPI for GetReturnDetailsByRetailerID which is used to show the return history for a particular retailer. It was creating some issue the reason of which may be that the method contain join of several tables. So I use Get for GetOrdersByRetailerID which retrives all the orders placed by a particular retailer. We used HttpClient method to consume WebAPI. I also faced issue while passing the retailer id to the method.
Deploying the MVC Project in Azure | 2 | 2 | 2019-11-21 | 2019-11-21

## Shreyash Pandey
Agile Task Board
|  | Assigned To: | Shreyash Pandey
|  | Use Case: | Admin And Address
|  | Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Introduction to DevOps | 2 | 3 | 2019-11-16 | 2019-11-16 | We were introduced to DevOps and it took time in giving access to each team
Introduction to Agile | 1.5 | 1.5 | 2019-11-18 | 2019-11-18 | We were introduced to Agile methodology and relevant concepts like sprints, backlogs and other mandatory terms of Scrum
Creating the necessary PLP Documents | 2 | 2 | 2019-11-19 | 2019-11-19 | There were certain documents like TEAM_URS, TEAMREGISTER, MINUTESOFMEETING, PRODUCTBACKLOG, SPRINTBACKLOG which are necessary in Agile Methodology. Documented the TEAM_URS document
Creating WebAPI and consuming it in MVC application | 5 | 6 | 2019-11-20 | 2019-11-21 | Created WebAPI for GetAllAddresses, GetAddressByAddressID, GetAddressByRetailerID
Deploying the MVC Project in Azure | 2 | 2 | 2019-11-21 | 2019-11-21 | There were issues with the commit limits and WebAPI stopping in between due to limited Azure resources.

## Sarthak
Agile Task Board
|  | Assigned To: | Sarthak Lav
|  | Use Case: | Retailer
|  | Team: | Team A
Task | Actual No. of Hours Expected | Actual No. of Hours | Start Date | End Date | Comments
Introduction to DevOps | 2 | 3 | 2019-11-16 | 2019-11-16 | We were introduced to DevOps and it took time in giving access to each team
Creating WireFrame for the project | 2 | 2 | 2019-11-16 | 2019-11-16 | Wire frame for few pages was created.
Introduction to Agile | 1.5 | 1.5 | 2019-11-18 | 2019-11-18 | We were introduced to Agile methodology and relevant concepts like sprints, backlogs and other mandatory terms of Scrum.
Creating the necessary PLP Documents | 2 | 2 | 2019-11-19 | 2019-11-19 | There were certain documents like TEAM_URS, TEAMREGISTER, MINUTESOFMEETING, PRODUCTBACKLOG, SPRINTBACKLOG which are necessary in Agile Methodology. Documented the TEAM_URS document.
Creating WebAPI and consuming it in MVC application | 3 | 4 | 2019-11-20 | 2019-11-21 | Created WebAPI for to show retailer profile and to register retailer. There were issues in consuming POST API while doing for first time.
Deploying the MVC Project in Azure | 2 | 2 | 2019-11-21 | 2019-11-21 | There were issues with the commit limits and WebAPI stopping in between due to limited Azure resources.